## Agenda
Sprint Planning Meeting: 02 |  |  |  | Notes:
Group Number: | 4 |  |  | Replace ## actual sprint planning number and group number respectively.
This spreadsheet contains more than one sheet; after you are done with Attendees information, complete information on sheet "Current Sprint"
Attendees (Last name, First Name) | Present | Absent | Notes/Comments | Complexity and number of items must be reasonable according to the number of team members.
K, Justin | X |  |  | Your professor might ask you to add more user stories and or increase complexity/functionality.
L, Willow | X |  |  | "Current Sprint" information will be used as a checklist to grade your sprint release.
C, Raemond | X
M, Christopher | X
Add a screenshot of your "Agile Task Board" below:

## Current Sprint
Sprint: 02 |  |  |  |  | Group Number: 4 |  | Notes:
Feel free to replace below table with your CSV export, make sure to format table as needed in order to support column filtering | [6 empty] | Bring information from your product backlog to identify "user stores" that will become part of your current sprint release. You can copy paste or replace table entirely using your CSV export. You can as change column names to match your format as needed.
Unique ID | Description (User Stories, Yellow Highlights are backlogs from previous sprint) |  |  |  | Status | Status
ID | Description (User Stories) | Column3 | Column4 | Column5 | Status
1 | As a Student, I want to browse a list of recipes, so I can make something affordable to eat |  |  |  | Done
2 | As a Student, I want to be able to share recipes, so other people can save money |  |  |  | In Progress
3 | As a Student, I want to be able to add my own recipes to the app, so I can use it later |  |  |  | On Hold
4 | As a student, I want to be able to add items to a list, so I can use it for grocery shopping |  |  |  | In Progress
5 | As a person on a diet, I want to be able to filter based on calorie count so that I can make sure I'm following my dietary needs. |  |  |  | In Progress
6 | As a person with allergies, I want to be able to filter based on allergies so that I can confirm all the ingredients are safe for me. |  |  |  | In Progress
7 | As a single mom, I want to easily find kid friendly recipes so that my children will enjoy the meals. |  |  |  | Done
8 | As a student, I want to easily find quick recipes so that I can make meals before classes. |  |  |  | Done
9 | As a student, I want to be able to filter based on price so that I can find meals within my budget range. |  |  |  | In Progress
10 | As a student or someone who is on a tight budget, I would like to know the amount of food serving or recipe I can make base of from what I have available. |  |  |  | In Progress
11 | As a user, I would like to know the ingredients I lack to be able to complete a recipe. |  |  |  | On Hold
12 | As a user, I would like to filter out recipes that I can make with what I have available based on if it is a vegan diet or not. |  |  |  | In Progress
13 | As a user who has a nutrient supplemental need, I would like to know the nutrients available on the filtered recipe. |  |  |  | On Hold
14 | As a user, I would like to be able to set a schedule on the recipe I would like to cook for that day and remind me the ingredients I need to buy to complete the recipe. |  |  |  | On Hold
15 | As a user, I would like to know the nearest store that has the ingredients I needed to complete the recipe I want to cook. |  |  |  | On Hold
16 | As a user, I would like to be able to register to the app and create my own profile. |  |  |  | Done
17 | As a user, I would like to favourite recipes so that I can find them quickly at another time |  |  |  | In Progress
18 | As a user, I would like to see recently viewed recipes so that I can quickly navigate back to them |  |  |  | On Hold
19 | As a user, I would like to hide recipes so that I can avoid recipes that I am not interested in |  |  |  | On Hold
20 | As a user, I would like to search for recipe titles so that I can find a specific recipe |  |  |  | Done
21 | As a user, I would like to search for ingredients so that I can view recipes that require that ingredient |  |  |  | On Hold
22 | As a user, I would like to filter recipes by total time required (prep + cook) so that I can make meals that fit into my busy schedule |  |  |  | In Progress
23 | As a user, I would like to filter recipes by complexity so that I know how difficult the recipe is to make |  |  |  | In Progress
24 | As a user, I would like there to be YouTube linked recipes, so I have the option to watch a video instead reading |  |  |  | In Progress

## Technology
Questions: | Answers
Front End Technology? | React JS
Are you using or plan to use a Data Base? | Yes
If Yes which DB engine are you using? | Firebase (Firestore)
Which application server are you using? | Nodejs
Describe here any additional technologies | Adobe Photoshop, XD
Additional Notes